## Sheet1
eLearning Design and Development
ADDIE Gantt Chart
SME：Subject Matter Expert (Instructional Designer)
GD：Graphic Designer
WM：Web Master
MS：Media Specialist.
Task | Person(s) | Start Date | Finish Date | Estims. Hrs | Spent. Hrs | Complete | March | March | March 31~ | April | April | April | April 28~ | May | May | May | Remark
| Responsible |  |  |  |  | % | 17~23 | 24~30 | 2014-04-06 | 7~13 | 14~20 | 21~27 | 2014-05-04 | 5~11 | 12~18 | 19~25
Work Weeks | [6 empty] | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Analysis |  | Week 1 | Week 2
Needs Analysis | SME | Mon 3/17/14 | Sun 3/23/14 | 20 | 18 | 100 | bar: Week 1
Course Analysis | SME | Mon 3/24/14 | Sun 3/30/14 | 20 | 22 | 100 | bar: Week 1
Design |  | Week 3 | Week 4
Content Design | SME/GD/ WM | Mon 3/24/14 | Sun 4/6/14 | 120 | bar: Week 2 to Week 3
Prototyping | SME/GD/ WM | Mon 3/24/14 | Sun 4/6/14 | 120 | bar: Week 2 to Week 3
Story Boarding | SME/GD/ WM | Mon 4/7/14 | Sun 4/13/14 | 60
Development |  | Week 5 | Week 5
Multimedia Production | MS | Mon 4/14/14 | Sun 4/27/14 | 20 | bar: Week 4
ID Testing | GD/ WM | Mon 4/14/14 | Sun 4/27/14 | 80 | bar: Week 5 to Week 6
Multimedia Revision | MS | Mon 4/21/14 | Sun 4/27/14 | 40 | bar: Week 5 to Week 6
Implementation |  | Week 7 | Week 8
LMS Integration | GD/ WM/ MS | Mon 4/28/14 | Sun 5/4/14 | 60 | bar: Week 7
SME Testing | GD/ WM | Mon 5/5/14 | Sun 5/11/14 | 40 | bar: Week 8
LEM Testing | GD/ WM | Mon 5/5/14 | Sun 5/11/14 | 40 | bar: Week 8
Evaluation |  | Week 9 | Week 10
Production Integration | SME | Mon 5/12/14 | Sun 5/18/14 | 20
Pilot Testing | SME | Mon 5/19/14 | Sun 5/25/14 | 20
LEGENDA
Not Started
In Progress | bar: Week 10
Completed | bar: Week 10
Pending Input | bar: Week 10
Deferred | bar: Week 10